## Sheet2
SPRINT PLANNING GROUP 7
PROJECT NAME : Mission: Highly Available! |  |  |  | PROJECT MANAGER |  | START DATE | END DATE | OVERALL PROGRESS | PROJECT DELIVERABLE |  | TEAM MEMBERS : Darren B, Jimmy R, Mohammad J, Sushma M
|  |  |  | Kent Burgdorfer |  | 2025-04-22 | 2025-05-20 | 98% | SCOPE STATEMENT
| TASK NAME | DELIVERABLES | FEATURE TYPE | RESPONSIBLE | STORY POINTS | START DATE | END DATE | DURATION in Days | STATUS | PRIORITY | COMMENTS
| SPRINT 1 : Sprint Plan |  |  |  | 100 | 2025-04-22 | 2025-04-24
| Task 1 | Defining Team Roles |  | Team | 5 | 2025-04-23 | 2025-04-24 |  | Complete | Medium
| Task 2 | Write User Stories and acceptance criteria |  | Sushma | 30 | 2025-04-22 | 2025-04-23 |  | Complete | High
| Task 3 | Breakdown tasks into backlog items |  | Team | 10 | 2025-04-22 | 2025-04-23 |  | Complete | High
| Task 4 | Create a timeline and assign responsibilities |  | Team | 5 | 2025-04-23 | 2025-04-24 |  | Complete | Medium
| Task 5 | AWS Account |  | All | 5 | 2025-04-22 | 2025-04-23 |  | Complete | High
| Task 6 | Sprint Plan Document |  | Darren | 30 | 2025-04-23 | 2025-04-24 |  | Complete | Medium
| Task 7 | Set up GitHub/GitLab repo |  | Sushma | 5 | 2025-04-22 | 2025-04-23 |  | Complete | High
| Task 8 | Choosing Project management tool |  | Team | 10 | 2025-04-23 | 2025-04-24 |  | Complete | Low
| SPRINT 2: CloudFormation Template (IaC) |  |  |  | 100 | 2025-04-25 | 2025-04-29
| Task 1 | Identifies and specifies the necessary resources for implementing a high availability (HA) architecture |  | Team | 15 | 2025-04-25 | 2025-04-26 |  | Complete | High
| Task 2 | Design logical architecture(VPC, EC2, RDS etc) |  | Team | 20 | 2025-04-25 | 2025-04-27 |  | Complete | High
| Task 3 | Create modular CloudFormation templates |  | Jimmy | 20 | 2025-04-25 | 2025-04-28 |  | Complete | High
| Task 4 | Inline comments in templates and add to GitHub with README version 1 |  | Jimmy | 10 | 2025-04-29 | 2025-04-29 |  | Complete | Low
| Task 5 | Deploys Primary Region N-Tier architecture (YAML or JSON with README.md) |  | Team | 20 | 2025-04-25 | 2025-04-28 |  | Complete | High
| Task 6 | Test stack deployment and parameterization |  | Mohammad | 15 | 2025-04-28 | 2025-04-29 |  | Complete | Medium
| SPRINT 3 : Primary Region Deployment |  |  |  | 100 | 2025-04-30 | 2025-05-06
| Task 1 | Deploys all stacks using CloudFormation |  | Team | 20 | 2025-04-30 | 2025-05-05 |  | Complete | High
| Task 2 | Confirm full connectivity: Web/App <->RDS |  | Jimmy | 30 | 2025-05-05 | 2025-05-05 |  | Complete | High
| Task 3 | Add sample front-end content and DB entries |  | Jimmy | 30 | 2025-04-30 | 2025-05-04 |  | Complete | High
| Task 4 | Test Functional web app with RDS backend in primary region (demo or screenshot) |  | Team | 20 | 2025-05-05 | 2025-05-06 |  | Complete | High
| SPRINT 4 : DR Region Deployment |  |  |  | 100 | 2025-05-07 | 2025-05-13
| Task 1 | Deployed DR stack with DNS/manual failover demonstration |  | Jimmy | 15 | 2025-05-07 | 2025-05-13 |  | Complete | High
| Task 2 | Replicate and modify templates for DR region |  | Jimmy | 15 | 2025-05-07 | 2025-05-13 |  | Complete | High
| Task 3 | Create cross-region RDS read replica |  | Jimmy | 10 | 2025-05-07 | 2025-05-13 |  | Complete | High
| Task 4 | Deploy Web/App tiers in DR region |  | Jimmy | 20 | 2025-05-07 | 2025-05-13 |  | Complete | High
| Task 5 | Set up Route 53 with health checks and failover policy |  | Team | 20 | 2025-05-07 | 2025-05-13 |  | Complete | High
| Task 6 | Simulate failure and verify auto redirection |  | Team | 10 | 2025-05-07 | 2025-05-13 |  | Complete | High
| Task 7 | Document RPO/RTO and capture failure proof (Video/screenshots) |  | Sushma | 10 | 2025-05-12 | 2025-05-13 |  | Complete | Medium
| SPRINT 5 : Final Submission & Presentation |  |  |  | 100 | 2025-05-14 | 2025-05-20
| Task 1 | Clean and organize all CloudFormation templates |  | Jimmy | 10 | 2025-05-14 | 2025-05-15 |  | Complete | High
| Task 2 | Finalize README.md and code comments |  | Jimmy | 10 | 2025-05-14 | 2025-05-15 |  | Complete | Medium
| Task 3 | Create architecture diagram (Lucidchart/draw.io) |  | Jimmy | 20 | 2025-05-14 | 2025-05-15 |  | Complete | High
| Task 4 | Record a 5-minute team presentation or slide deck |  | Sushma | 30 | 2025-05-15 | 2025-05-20 |  | Complete | High
| Task 5 | Write final summary report |  | Team | 10 | 2025-05-15 | 2025-05-20 |  | Complete | Medium
| Task 6 | Submit GitHub repo, demo media, and final documentation |  | Sushma | 20 | 2025-05-15 | 2025-05-20 |  | Complete | High